## SHENTEL STREET SHEET
[6 empty] | VATI X County |  | DAMAGE & COMPLAINT CONTACT INFORMATION Phone: (866) 997-6474 External D&C Link: https://glofiber.com/construction/contact-us
DATE MM-DD-YYYY | STREET ADDRESS/INTERSECTION2 | County | Project Number | DSA | ROW PERMIT# | MISS UTILITY TICKET NUMBER | TYPE OF WORK | MAIN CONTRACTOR | MAIN CONTRACTOR CONTACT | SUB-CONTRACTOR | SHENTEL FIELD CONTACT
11.4.24 | Brown's Mill Rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 |  | UG | Accutech | Nate McCue | OZ Communications | Tim Thompson
11.4.24 | Stone Rd. | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 |  | UG | Accutech | Nate McCue | OZ Communications | Tim Thompson
Week of 11/18/2024 | Elliot rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 |  | Aerial | Accutech | Nate McCue | Oz Communications | Tim Thompson
Week of 11/18/2024 | East Ferry rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 |  | Aerial | Accutech | Nate McCue | Oz Communications | Tim Thompson
Week of 11/25/2024 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 |  | Aerial | Accutech | Nate McCue | Oz Communications | Tim Thompson
Week of 11/25/2024 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 | B432400993 | Underground | Accutech | Nate McCue | SLP Construction | Tim Thompson
Week of 11/25/2024 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 | B432401137 | Underground | Accutech | Nate McCue | SLP Construction | Tim Thompson
Week of 11/25/2024 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 | B432401231 | Underground | Accutech | Nate McCue | SLP Construction | Tim Thompson
Week of 11/25/2024 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 | B432401279 | Underground | Accutech | Nate McCue | SLP Construction | Tim Thompson
Week of 11/25/2024 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 | B432401474 | Underground | Accutech | Nate McCue | SLP Construction | Tim Thompson
Week of 12/02/2024 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 |  | Aerial | Accutech | Nate McCue | Oz Communications | Tim Thompson
Week of 12/02/2024 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 | B432400993 | Underground | Accutech | Nate McCue | SLP | Tim Thompson
Week of 12/02/2024 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 | B432401137 | Underground | Accutech | Nate McCue | SLP | Tim Thompson
Week of 12/02/2024 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 | B432401231 | Underground | Accutech | Nate McCue | SLP | Tim Thompson
Week of 12/02/2024 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 | B432401279 | Underground | Accutech | Nate McCue | SLP | Tim Thompson
Week of 12/02/2024 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 | B432401474 | Underground | Accutech | Nate McCue | SLP | Tim Thompson
Week of 12/02/2024 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 | B432401616 | Underground | Accutech | Nate McCue | SLP | Tim Thompson
Week of 12/02/2024 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 | B432401616 | Underground | Accutech | Nate McCue | SLP | Tim Thompson
Week of 12/02/2024 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 | B432401642 | Underground | Accutech | Nate McCue | SLP | Tim Thompson
Week of 12/9/2024 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 |  | Aerial | Accutech | Nate McCue | Oz Communications | Tim Thompson
Week of 12/9/2024 | Stone dr | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 | A434000954 | Underground | Accutech | Nate McCue | SLP | Tim Thompson
Week of 12/9/2024 | Stone dr | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 | B432402036 | Underground | Accutech | Nate McCue | SLP | Tim Thompson
Week of 12/23/24 | Stone rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 |  | Splicing | Accutech | Nate McCue | Costa Lima | Tim Thompson
Week of 12/23/24 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 |  | Splicing | Accutech | Nate McCue | Costa Lima | Tim Thompson
Week of 12/23/24 | E Ferry rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 |  | Splicing | Accutech | Nate McCue | Costa Lima | Tim Thompson
Week of 01/06/2025 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 |  | Aerial | Accutech | Nate McCue | GM Communications | Tim Thompson
Week of 01/06/2025 | Browns Mill rd | Campbell | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 |  | Splicing | Accutech | Nate McCue | Costa Lima | Tim Thompson
Monday, January 20, 2025 | BROWNS MILL RD, E FERRY RD, STONE RD, GOUGH RD, | CAMPBELL | PRJ51-5516 | GLADVA.DSA.003 | 320-36945 |  | Splicing | Accutech | Nate McCue | Costa Lima LLC | Bradley Purser

## Sheet1 (hidden)
Bedford Counties: | Bedford
BDFDVA.DSA.001 A | Campbell
BDFDVA.DSA.001 B | Franklin
BDFDVA.DSA.002 | Frederick
BDFDVA.DSA.003 | Grant
BDFDVA.DSA.004 | Roanoke
BDFDVA.DSA.005 | Shenandoah
BDFDVA.DSA.006
BDFDVA.DSA.007
BDFDVA.DSA.008
BGISVA.BB.001
BGISVA.DSA.001
BGISVA.DSA.002
BGISVA.DSA.003
BGOTVA.BB.001
BGOTVA.DSA.001
BGOTVA.DSA.002
BGOTVA.DSA.003
BGOTVA.DSA.004
GOODVA.DSA.001
GOODVA.DSA.002
GOODVA.DSA.003
GOODVA.DSA.004
GOODVA.DSA.005
GOODVA.DSA.006
HDDLVA.BB.001
HDDLVA.DSA.001
HDDLVA.DSA.002
MTVLVA.BB.001
MTVLVA.DSA.001
MTVLVA.DSA.002
MTVLVA.DSA.003
MTVLVA.DSA.004
********************
Campbell Counties:
ALTAVA.DSA.001
ALTAVA.DSA.002
ALTAVA.DSA.003
ALTAVA.DSA.004
CONCVA.DSA.001
CONCVA.DSA.002
CONCVA.DSA.003
GLADVA.BB.001
GLADVA.DSA.001
GLADVA.DSA.002
GLADVA.DSA.003
GLADVA.DSA.004
GLADVA.DSA.005
RUBGVA.DSA.001
RUBGVA.DSA.002
RUBGVA.DSA.003
RUBGVA.DSA.004
RUBGVA.DSA.005 (TEST)
RUBGVA.DSA.006
RUBGVA.DSA.007
RUBGVA.DSA.008
RUBGVA.DSA.009
*******************
Franklin Counties:
BNMLVA.DSA.004
BNMLVA.DSA.001
BNMLVA.DSA.002
BNMLVA.DSA.003
WTLKVA.DSA.001
BNMLVA.DSA.004
HRDYVA.DSA.004 Wysong A, B & C 2021
VFRDWD.DSA.006 2021 (Long Horn)
FERMVA.DSA.008
HRDYVA.DSA.003
HRDYVA.DSA.002
HRDYVA.DSA.001
RDWDVA.DSA.005
FERMVA.DSA.001
FERMVA.DSA.002
FERMVA.DSA.003
FERMVA.DSA.004
FERMVA.DSA.005
FERMVA.DSA.006A
FERMVA.DSA.006B
FERMVA.DSA.007
RDWDVA.DSA.001
RDWDVA.DSA.002
RDWDVA.DSA.003
RDWDVA.DSA.004
*****************
Frederick Counties:
SABIMD.DSA.001
SABIMD.DSA.002
SABIMD.DSA.003
ROCKMD.BB.001
ROCKMD.DSA.001
ROCKMD.DSA.002
ROCKMD.DSA.003
ROCKMD.DSA.004
ROCKMD.DSA.005
ROCKMD.DSA.006
ADAMMD.DSA.001
ADAMMD.DSA.002
ADAMMD.DSA.003
UNIOMD.BB
UNIOMD.DSA.001
UNIOMD.DSA.002
UNIOMD.DSA.003
UNIOMD.DSA.004
UNIOMD.DSA.005
UNIOMD.DSA.006
*****************
Grant Counties:
PTBGWV.DSA.001
PTBGWV.DSA.002
******************
Roanoke Counties:
SALMVA.DSA.001
TMBKVA.DSA.003 (2023)
FTVYVA.DSA.003 (2023)
FTVYVA.DSA.004 (2023)
FTVYVA.DSA.005 (2023)
EDBGVA.DSA.001_ (2022)
BASYVA.DSA.001_
BASYVA.DSA.002_
BASYVA.DSA.003_
TMBKVA.BB.001
TMBKVA.DSA.006 (2022)
EDBGVA.DSA.003 (2023)
EDBGVA.DSA.005 (2023)
EDBGVA.DSA.006 (2023)
EDBGVA.DSA.003 (2022)
EDBGVA.DSA.005 (2022)
EDBGVA.DSA.002_ (2022)
MTJCVA.DSA.011 (2022)
EDBGVA.DSA.002 (2023)
STBGVA.DSA.011
STBGVA.DSA.001_
STBGVA.DSA.002_
TMBKVA.DSA.004 (2023)
TMBKVA.DSA.005 (2023)
TMBKVA.DSA.006 (2023)
STBGVA.DSA.006 (2023)
STBGVA.DSA.007 (2023)
STBGVA.DSA.008 (2023)
STBGVA.DSA.009 (2023)
STBGVA.DSA.010 (2023)
STBGVA.DSA.005 (2023)
MTJCVA.DSA.002_ (2022)
NWMRVA.DSA.001 (2022)
FTVYVA.DSA.002 (2023)
WDSTVA.DSA.002 (2022)
TMBKVA.DSA.004 (2022)
TMBKVA.DSA.005 (2022)
STBGVA.DSA.005 (2022)
STBGVA.DSA.006 (2022)
STBGVA.DSA.007 (2022)
STBGVA.DSA.008 (2022)
STBGVA.DSA.009 (2022)
STBGVA.DSA.010 (2022)
FTVYVA.DSA.005 (2022)
STBGVA.DSA.003_
STBGVA.DSA.004_
FTVYVA.DSA.002 (2022)
FTVYVA.DSA.003 (2022)
FTVYVA.DSA.004 (2022)
MTJCVA.DSA.010
MTJCVA.DSA.003 (2022)
MTJCVA.DSA.004 (2022)
MTJCVA.DSA.005 (2022)
MTJCVA.DSA.006 (2022)
MTJCVA.DSA.007 (2022)
MTJCVA.DSA.008 (2022)
MTJCVA.DSA.009 (2022)
MTJCVA.DSA.001 (2023)
MTJCVA.DSA.002 (2023)
MTJCVA.DSA.003 (2023)
MTJCVA.DSA.004 (2023)
MTJCVA.DSA.005 (2023)
MTJCVA.DSA.006 (2023)
MTJCVA.DSA.007 (2023)
MTJCVA.DSA.008 (2023)
MTJCVA.DSA.009 (2023)
MTJCVA.DSA.010 (2023)
FTVYVA.DSA.001 (2022)
WDSTVA.DSA.001 (2022)
WDSTVA.DSA.003 (2022)
WDSTVA.DSA.003 (2023)
WDSTVA.DSA.001 (2023)
WDSTVA.DSA.002 (2023)
TMBKVA.DSA.002_
TMBKVA.DSA.003 (2022)
NWMRVA.DSA.002 (2022)
NWMRVA.DSA.003 (2022)
NWMRVA.DSA.004 (2022)
NWMRVA.DSA.005 (2022)
NWMRVA.DSA.006 (2022)
NWMRVA.DSA.001 (2023)
NWMRVA.DSA.002 (2023)
NWMRVA.DSA.003 (2023)
NWMRVA.DSA.004 (2023)
NWMRVA.DSA.005 (2023)
NWMRVA.DSA.006 (2023)