## SHENTEL STREET SHEET
[6 empty] | VATI Campbell County |  | DAMAGE & COMPLAINT CONTACT INFORMATION Phone: (866) 997-6474 External D&C Link: https://glofiber.com/construction/contact-us
DATE MM-DD-YYYY | STREET ADDRESS/INTERSECTION2 | County | Project Number | Node | ROW PERMIT# | MISS UTILITY TICKET NUMBER | TYPE OF WORK | MAIN CONTRACTOR | MAIN CONTRACTOR CONTACT | SUB-CONTRACTOR | SHENTEL FIELD CONTACT
2025-06-02 | DOVE DR | Campbell | PRJ51-6222 | VATI_Campbell_RU048 |  |  | splicing/waiting on p/s | JCL INC | HUNTER GILLISPIE 434-660-6500 |  | JOEY GARICA
2025-06-02 | murrel lane | Campbell | PRJ51-6250 | VATI_Campbell_RU005 |  |  | aer/UG | JCL INC | HUNTER GILLISPIE 434-660-6500 |  | JOEY GARICA
2025-06-02 | howards manor | Campbell | PRJ51-6208 | VATI_Campbell_RU022 |  |  | ug/ splicing | JCL INC | HUNTER GILLISPIE 434-660-6500 |  | JOEY GARICA
2025-06-02 | town fork | Campbell | PRJ51-6236 | VATI_Campbell_RU077 |  |  | ug/ splicing | JCL INC | HUNTER GILLISPIE 434-660-6500 |  | JOEY GARICA
2025-06-02 | leesville road | Campbell | PRJ51-6224 | VATI_Campbell_RU050 |  |  | ug/ splicing | JCL INC | HUNTER GILLISPIE 434-660-6500 |  | JOEY GARICA
2025-06-02 | Red House | Campbell | PRJ51-6204 | VATI_Campbell_RU001 |  |  | aer/UG | JCL INC | HUNTER GILLISPIE 434-660-6500 |  | JOEY GARICA
2025-06-02 | Eastbrook road | Campbell | PRJ51-6214 | VATI_Campbell_RU033 |  |  | aer/UG | JCL INC | HUNTER GILLISPIE 434-660-6500 |  | JOEY GARICA
2025-06-02 | RIVERBEND ROAD | Campbell | PRJ51-6247 | VATI_Campbell_RU038 |  |  | AER | JCL INC | HUNTER GILLISPIE 434-660-6500 |  | JOEY GARICA

## Sheet1 (hidden)
Bedford Counties: | Bedford
VATI_Bedford_BF001 | Campbell
VATI_Bedford_BF002 | Franklin
VATI_Bedford_BF003 | Shenandoah
VATI_Bedford_BF004
VATI_Bedford_BF005
VATI_Bedford_BF006
VATI_Bedford_BF007
VATI_Bedford_BF008
VATI_Bedford_BF015
VATI_Bedford_BF017
VATI_Bedford_BF018
VATI_Bedford_BF019
VATI_Bedford_BF022
VATI_Bedford_BF023
VATI_Bedford_BF024
VATI_Bedford_GC001
VATI_Bedford_RU003
VATI_Bedford_RU009
VATI_Bedford_RU010
VATI_Bedford_RU011
VATI_Bedford_RU015
VATI_Bedford_RU016
VATI_Bedford_RU017
VATI_Bedford_RU018
VATI_Bedford_RU019
VATI_Bedford_RU020
VATI_Bedford_RU021
VATI_Bedford_RU024
VATI_Bedford_RU025
VATI_Bedford_RU026
VATI_Bedford_RU028
VATI_Bedford_RU051
VATI_Bedford_RU062
VATI_Bedford_RU064
VATI_Bedford_RU069
VATI_Bedford_RU072
VATI_Bedford_RU075
VATI_Bedford_RU076
VATI_Bedford_RU084
VATI_Bedford_RU088
VATI_Bedford_RU091
VATI_Bedford_RU092
VATI_Bedford_RU093
VATI_Bedford_RU095
VATI_Bedford_RU097
************************
Campbell Counties:
VATI_Campbell_RO051
VATI_Campbell_RU001
VATI_Campbell_RU002
VATI_Campbell_RU003
VATI_Campbell_RU004
VATI_Campbell_RU005
VATI_Campbell_RU006
VATI_Campbell_RU007
VATI_Campbell_RU008
VATI_Campbell_RU012
VATI_Campbell_RU013
VATI_Campbell_RU014
VATI_Campbell_RU022
VATI_Campbell_RU023
VATI_Campbell_RU029
VATI_Campbell_RU030
VATI_Campbell_RU031
VATI_Campbell_RU032
VATI_Campbell_RU033
VATI_Campbell_RU034
VATI_Campbell_RU035
VATI_Campbell_RU036
VATI_Campbell_RU037
VATI_Campbell_RU038
VATI_Campbell_RU039
VATI_Campbell_RU042
VATI_Campbell_RU043
VATI_Campbell_RU044
VATI_Campbell_RU045
VATI_Campbell_RU046
VATI_Campbell_RU047
VATI_Campbell_RU048
VATI_Campbell_RU049
VATI_Campbell_RU050
VATI_Campbell_RU054
VATI_Campbell_RU057
VATI_Campbell_RU058
VATI_Campbell_RU059
VATI_Campbell_RU061
VATI_Campbell_RU068
VATI_Campbell_RU074
VATI_Campbell_RU077
VATI_Campbell_RU078
VATI_Campbell_RU080
VATI_Campbell_RU081
VATI_Campbell_RU085
VATI_Campbell_RU087
VATI_Campbell_RU090
VATI_Campbell_RU098
VATI_Campbell_RU099
VATI_Campbell_RU101
*******************
Franklin Counties:
VATI_Franklin_RE040
VATI_Franklin_RE030
VATI_Franklin_RE027
VATI_Franklin_RE043
VATI_Franklin_RE035
VATI_Franklin_RE069
VATI_Franklin_RE075
VATI_Franklin_RE029
VATI_Franklin_RE028
VATI_Franklin_RE032
VATI_Franklin_RE042
VATI_Franklin_RE091
VATI_Franklin_RE044
VATI_Franklin_WG001
VATI_Franklin_RE090
VATI_Franklin_RE092
VATI_Franklin_RE045
VATI_Franklin_RE031
VATI_Franklin_RE059
VATI_Franklin_RE056
VATI_Franklin_RE057
VATI_Franklin_RE033
VATI_Franklin_BU001
VATI_Franklin_RE053
VATI_Franklin_RE020
VATI_Franklin_RE048
VATI_Franklin_RE049
VATI_Franklin_RE081
VATI_Franklin_RE054
VATI_Franklin_RE052
VATI_Franklin_RE073
VATI_Franklin_RE055
VATI_Franklin_RE015
VATI_Franklin_RE074
VATI_Franklin_RE037
VATI_Franklin_RE017
VATI_Franklin_RE082
VATI_Franklin_RE076
VATI_2021_Old Farm Road_RE079
VATI_Franklin_RE050
VATI_Franklin_RE038
VATI_Franklin_RE039
VATI_Franklin_2022_RE062_Phase II
VATI_Franklin_2022_RE071_Phase II
VATI_Franklin_2022_RE069_Phase II
VATI_Franklin_2022_RE058_Phase II
VATI_Franklin_2022_RE078_Phase II
VATI_Franklin_2022_RE070_Phase II
VATI_Franklin_2022_RE066_Phase II
Hardy Cabinet (VATI) - Memorial Baptist Pole
VATI_Franklin_RE008
VATI_Franklin_RE021
VATI_Franklin_RE022
VATI_Franklin_RE084
VATI_Franklin_RE025
VATI_2021_Woods Edge Dr_RE034
VATI_Franklin_RE036
VATI_Franklin_RE003
VATI_Franklin_RE005
VATI_Franklin_RE006
VATI_Franklin_RE013
VATI_Franklin_RE002
VATI_Franklin_RE034
VATI_Franklin_RE047
VATI_Franklin_RE041
VATI_Franklin_RE026
VATI_Franklin_RE014
VATI_Franklin_RE077
VATI_Franklin_RE078
VATI_Franklin_RE070
VATI_Franklin_RE066
VATI_Franklin_RE067
VATI_Franklin_RE068
VATI_Franklin_RE062
VATI_Franklin_RE064
VATI_Franklin_RE065
VATI_Franklin_RE087
VATI_Franklin_RE001
VATI_Franklin_RE063
VATI_Franklin_Wysong D 2021
*****************
Shenandoah Counties:
VATI_Shenandoah_Clary_Rd_GPON (2023)
VATI_Shenandoah_ED008 (2022)
VATI_Shenandoah_ED010 (2022)
VATI_Shenandoah_ED011 (2022)
VATI_Shenandoah_ED012 (2022)
VATI_Shenandoah_ED013 (2022)
VATI_Shenandoah_ED023 (2022)
VATI_Shenandoah_ED029 (2022)
VATI_Shenandoah_ED030 (2022)
VATI_Shenandoah_MJ_RFoG (2023)
VATI_Shenandoah_NM005 (2023)
VATI_Shenandoah_NM006 (2023)
VATI_Shenandoah_NWMRVA.Hayneswood_Ln_GPON (2023)
VATI_Shenandoah_NWMRVA.Quicksburg_Rd_RFoG (2023)
VATI_Shenandoah_ST008 (2023)
VATI_Shenandoah_ST009 (2022)